Sample Project Management Plan- Bathroom Renovation

Scope baseline:

- What scope or boundaries are included? - Renovate master bathroom and children’s bathroom - Demolish old shower and flooring down to subfloor - Uninstall toilet and vanity - Upgrade wiring and power outlets - Change light fixtures and sockets - Replace sink and plumbing - Install new toilet, shower pan, shower door, shower tile, plumbing fixtures - Lay new flooring - Install backsplash at sink - Install new vanity, fixtures, and mirror - Paint - Hang new curtains - What scope or boundaries are not included? - The bathroom windows will not be replaced - The bathroom fans and doors will not be replaced - What requires further definition in discover phases? - Final selections of vanities, flooring, tile, and hardware are needed - Contractor interviews - What regulatory or other requirements will be accomplished? - Permits and inspections by city representatives as needed - The homeowners and other stakeholders (their children) will temporarily live at their second house once the renovations begin - Contractors will be paid a flat fee vs. an hourly rate

Schedule baseline

- Month 1-Develop design, project plan and select contractors - Month 1-Order materials - Month 2/3-Install equipment/flooring - Month 3 Test/verify - Month 3-Close out/pay contractors

Cost baseline

- Total cost not to exceed $15,000

Scope management plan:

- The scope has been defined by the customers (homeowners) and confirmed via the charter/contract. Any deviations in the original scope will be documented via a change order by the respective contractor which must be approved by the homeowners prior to proceeding. All changes will be tracked by the project manager.

Requirements management plan:

- The project manager will document the customer’s requirements via the charter/contract. - Any approved changes will be documented and tracked by the project manager and associated contractor via the change, risk, issue, and decision log.

Schedule management plan:

- The schedule will be created and tracked by the project manager using Microsoft Project. It will be updated weekly at a minimum and shared with the customers.

Cost management plan:

- Cost will be managed via a weekly spending report which will be provided by each contractor and submitted to the project manager for tracking. Each contractor will alert the project manager immediately if cost overruns are anticipated prior to the overage occurring. Any exceptions to the original spending plan must be submitted to the project manager and approved by the customers.

Quality management plan

- Expected quality standards have been defined by the customers as follows:

- Only new materials will be used for the renovations - All materials will be installed per customer selections - Plumbing will be secure and free of leaks - Tiles and mosaic will have grout and caulking uniformly and completely applied - All drawers and doors will be tightly secured and operate with a full range of motion - The shower head flow rate will be in energy saver mode (8-10 liters/minute) - The toilets will have a dual flush option to save water - Customers and contractors will test each system (electrical, plumbing, hardware) via a walkthrough and operational assessment. Any defects or outages will be documented and corrected by the contractor prior to signing off on the work and issuing payment.

Process improvement plan:

- Each week the project manager and customers will discuss whether the communication, approach to completing the work, or any other elements need to be modified and make changes as needed

Human resource management plan:

- Contractors will be utilized to perform the renovations - The project manager will coordinate interviews and selection of all contractors with approval from the customers - Once the baseline staffing is determined, any changes to the plan must be approved by the homeowners

Communications management plan:

- During the Business Case, Discovery and Game Plan phases, communication will occur weekly via an email update from the project manager to the customers. - The contractors will communicate directly to the project manager on a weekly basis unless specific input is needed between the contractors and homeowners - During the execution (carrying out the plan) phase, a daily verbal update will be shared by each contractor with the project manager as the renovations are being completed. The project manager will provide a daily summary of progress made via email and follow up with a phone call as needed

Risk management plan:

- Newly identified risks and issues will be communicated immediately to the project manager who will document them along with a response strategy. Updates will be shared with the homeowners by the project manager each time a new issue or risk is identified unless it is resolved during the same workday - The change, risk, issue, decision log will be used for documentation and maintained by the project manager

Procurement management plan:

- The project manager will coordinate quotes from vendors and the selection process - The project manager will order any materials not directly supplied by the contractors - The manager will maintain a detailed spreadsheet of all quotes and purchases along with tracking spending against the budget

Stakeholder management plan:

- The stakeholder management plan was documented separately